## Control
AGI TR — Transport prep & document milestones (control)
Trip / Cycle (e.g. TR5) | TRn (user)
D0 = Planned load-out date (anchor) | 2026-04-26
D_sail (optional; sail-away anchor)
D_agi_loadin (optional)
Notes | Planned_Due in Master = D0 + Offset_days. Official HM/Maqta/ADNOC dates override any template. Cross-ref: AGI_TR_Submission_Documents_Milestone_Tracker (WhatsApp), AGI_TR_Submission_Milestones (PTW/V2), AGI_Email_Document_Submission_Milestone_FINAL (email).

## TR_Prep_Master
No | Gate | Phase | Package | Document_or_Submission | When_to_submit_rule | Offset_days_vs_D0 | Planned_Due | Owner_Prepare | Owner_Submit_Track | Approver_or_Verify | Priority | Hold_Y | DOC_ID | Evidence_IDs | Risk_if_missing | Next_action_hint
1 | G0 | Prep / Engineering | Engineering | Ramp / Linkspan certificate (survey) | D-7~D-2; each voyage if changed | -5 |  | Mammoet / Inspector / Aries | OFCO | HM / Port / MWS | Critical | Y | DOC-001 | E001;E017;E018 | PTW/load-out hold | Chase inspector-signed pack; revision-control
2 | G0 | Prep / Engineering | MWS | MWS confirmation / suitability (bow strength) | Before loading / D0 hold | -1 |  | MWS / Aries / Samsung | OFCO / Samsung | HM / MWS | Critical | Y | DOC-011 | E004;E038 | Load-out No-Go | Separate from COA; file formal confirmation
3 | G1 | Permit / Meeting | Permit | PTW — Hot Work | D-5~D-1; voyage/trip-wise | -3 |  | OFCO / Samsung / Mammoet | OFCO submit | Maqta / AD Ports HSE / HM | Critical | Y | DOC-002 | E018;E069 | Hot work stop | Validity cover slip + shift extension
4 | G1 | Permit / Meeting | Permit | PTW — Working Over Water | D-5~D-1; voyage/trip-wise | -3 |  | OFCO / Samsung / Mammoet | OFCO submit | Maqta / AD Ports HSE / HM | Critical | Y | DOC-003 | E018;E066 | Ramp/jetty interface stop | Bundle with marine PTW set
5 | G1 | Permit / Meeting | Permit | Land PTW / SPMT heavy transport | D-5~D0; trip-wise | -2 |  | OFCO / Samsung | OFCO submit | Maqta / AD Ports | Critical | Y | DOC-004 | E007;E067;E074 | No SPMT move | Do not assume prior trip reuse
6 | G1 | Permit / Meeting | HSE / Ops | MOS / MS (load in&out) | D-10~D-5; HM comments | -7 |  | Mammoet | Samsung / OFCO | ADNOC / HM | High | N | DOC-005 | E008;E085 | Approval delay | Single revision set with RA
7 | G1 | Permit / Meeting | HSE / Ops | Risk Assessment / JSA | D-5 before pre-op | -4 |  | Mammoet / Samsung | OFCO | HSE / HM | High | N | DOC-006 | E022;E045 | PTW reject | Match MOS revision
8 | G1 | Permit / Meeting | Cargo | Stowage Plan | D-5 before load-out mtg | -4 |  | Mammoet / Eng | OFCO | HM / MWS | High | N | DOC-007 | E045 | Deck review delay | With drawings one pack
9 | G1 | Permit / Meeting | Meeting | Pre-ops / FRA minutes | D-4~D-1 | -3 |  | OFCO / Samsung / Mammoet | OFCO circulate | AD Ports / HM / HSE | High | N | DOC-020 | E021;E052 | Approval drift | Store minutes + action IDs
10 | G2 | Load-out readiness | Access | Gate pass / CICPA / operator access | D-2~D0 | -1 |  | OFCO / Samsung / Mammoet | OFCO apply | Port security | Critical | Y | DOC-018 | E032;E073 | Crew lockout | Per-person + operator list
11 | G2 | Load-out readiness | Port | Berth request / allocation / Maqta update | D-2~D0 | -1 |  | OFCO / LCT / Port Ops | OFCO | MZP / VTS / Maqta | Critical | N | DOC-019 | E023;E053 | Schedule slip | Lay-by risk note
12 | G2 | Load-out readiness | Tide / Wx | Tide window + weather forecast | Daily + D0 AM | -1 |  | Mammoet / LCT / Port | OFCO share | MWS / HM / Samsung | Critical | Y | DOC-021 | E034;E077 | No-Go | Observed vs forecast log
13 | G2 | Load-out readiness | Equipment | Equipment booking (crane/fork/MAFI/gang) ≥24h | D-1 / 24h before | -1 |  | Mammoet / OFCO / Port | OFCO book | GC Ops | Medium | N | DOC-023 | E051;E062 | Standby cost | Release/off-hire evidence
14 | G2 | Load-out readiness | Cargo | Cargo drawings / loading drawings | D-5 | -4 |  | Mammoet / Eng | OFCO | HM / MWS | Medium | N | DOC-009 | E045 | Queries | Align to stowage
15 | G3 | Load-out / securing | Marine | Toolbox talk + attendance | Before each operation | 0 |  | Mammoet / Samsung / MWS | OFCO file | HSE / MWS | High | N | DOC-024 | E009 | Start gate | D0 first task
16 | G3 | Load-out / securing | Sea fastening | Sea fastening certificate / sail-away readiness | After lashing / before sail | 0 |  | Mammoet / LCT Master / MWS | OFCO | AGI / HM | Critical | Y | DOC-012 | E011;E055 | Cast-off delay | LCT Master sign-off chain
17 | G3 | Load-out / securing | Inspection | Lashing completion / LCT Master inspection | After load-out | 0 |  | Mammoet / LCT | Samsung / MWS | HM | Critical | Y | DOC-025 | E012;E089 | Sail-away fail | Photo + checklist
18 | G4 | Sail-away | Cargo | Manifest (final) + voyage number | Before cast-off | 0 |  | Samsung / Shipping / LCT | OFCO / Customs | HM / AGI | Critical | Y | DOC-008 | E039;E043 | Cast-off / AGI prep | Revision freeze
19 | G4 | Sail-away | MWS | MWS COA (voyage) | Prior sailing | 0 |  | MWS (NAS) | OFCO / Samsung | HM / LCT | Critical | Y | DOC-010 | E003;E006;E013 | Departure stop | Not same as suitability memo
20 | G4 | Sail-away | Marine | Vessel sailing consent | Before cast-off | 0 |  | OFCO / LCT / HM | OFCO | HM / VTS | High | N | DOC-013 | E044 | Clearance delay | Bundle COA+manifest
21 | G4 | Sail-away | Customs | Custom exit / clearance evidence | Before cast-off | 0 |  | Samsung / OFCO / Customs | OFCO | Port / Customs | High | N | DOC-014 | E040 | Hold | Match manifest
22 | G4 | Sail-away | Marine | Voyage plan / ETA notice | Pre-sail + arrival | 0 |  | LCT / OFCO / Samsung | OFCO | AGI / VTS | Medium | N | DOC-015 | E043 | Coordination | ETA log
23 | G5 | AGI load-in | AGI | LOP (linkspan-only scope typical) | Before AGI offload | 2 |  | ALS / SCT / Mammoet | OFCO | AOF SPA / ADNOC | High | N | DOC-016 | E014;E015 | Lifting stop | Confirm scope vs site rule
24 | G5 | AGI load-in | AGI | ADNOC approved TPC / lifting cert | Before AGI lifting | 2 |  | Mammoet / Lifting | OFCO | ADNOC | High | Y | DOC-017 | E016 | No lift | TPC register per item
25 | G5 | AGI load-in | AGI | AGI berth / load-in plan / site readiness | Before arrival | 1 |  | Samsung / AGI / LCT | AGI team | AGI HM / ADNOC | High | N | DOC-026 | E041;E086 | Offload delay | Security override note
26 | G6 | Return / next TR | Demob | MOS/PTW updates for next cycle | D+3~D+7 | 5 |  | Mammoet / Samsung | OFCO | HM / HSE | High | N | DOC-005;DOC-022 | E085 | Next TR delay | Lessons: FW/ballast in MOS
27 | G1 | Commercial / NOC | NOC | NOC support pack (license, award letter, RA+ERP) | As per AD Maritime gate | -5 |  | Samsung | OFCO | AD Maritime | High | N | (MS-027~041 pattern) |  | NOC block | From email milestone pack
28 | G0 | Vessel / PAN | PAN / ATLP | PAN set (crew list, registry, nav license, MDOH…) | Before MZP berthing declare | -10 |  | LCT / Master | OFCO | Port | High | Y | (MS-007) | msg-65 | Berth stall | ATLP reference store
29 | Idea | Governance | SSOT | Document revision matrix (supersedes) | Continuous |  |  | Doc controller (Samsung/OFCO) | Shared drive | All | Medium | N |  |  | Wrong revision on jetty | One PDF name rule + watermark
30 | Idea | Governance | Evidence | Email + portal receipt IDs in one column | Each submit |  |  | Submitter | OFCO archive | Internal | Medium | N |  |  | Dispute | Pastes Maqta ref #
31 | Idea | Ops | 24h rule | Port equipment requests | D-1 18:00 style deadline | -1 |  | Mammoet | OFCO | GC Ops | High | N |  | E062 | Standby | Countdown plan ties PTW shifts
32 | Idea | Permit | Validity overlap | PTW pack covers weather slip (+7d buffer) | When scheduling | -7 |  | OFCO / Mammoet | OFCO | HSE | High | N |  | E019 | Expiry mid-ops | Mammoet 1-week permit lesson

## Gate_Checklist
Gate | Phase | Typical_timing | Milestone_check | Linked_DOC_ids | Owner_of_integrated_pack
G0 | Prep / Engineering | D-14~D-7 | Linkspan cert path; MWS suitability; engineering basis | DOC-001;DOC-011 | Samsung / Mammoet lead; OFCO interface
G1 | Permit / Meeting | D-5~D-1 | PTW x3; MOS/RA; pre-op/FRA; berth plan | DOC-002~007;020 | OFCO submit; Mammoet/Samsung draft
G2 | Load-out readiness | D0 AM | Gate pass; equipment; tide/weather; MWS attendance; LCT alongside | DOC-018;019;021;023 | OFCO + Port Ops
G3 | Load-out / securing | D0 | Ramp crossing; lashing; sea fastening; inspections | DOC-012;024;025 | Mammoet + LCT
G4 | Sail-away | D0/D+1 | Manifest; customs exit; voyage #; sailing consent; COA | DOC-008;010;013~015 | OFCO + MWS + Customs
G5 | AGI load-in | D+1~D+3 | LOP/TPC; AGI berth; offload method | DOC-016;017;026 | Samsung AGI team + ALS
G6 | Return / next TR | D+3~D+7 | Demob/remob; next TR MOS/PTW refresh | DOC-005;022;027 | Mammoet / OFCO

## RACI_by_party
Party | Primary_roles | Typical_submit_track | Typical_prepare_review
OFCO | Port/HM interface; PTW submission; gate pass; berth; evidence archive | Submit/track to Maqta/HM/Port | Receipts, portal refs
Samsung / SCT | Owner docs; NOC support; coordination; AGI site | Sign indemnities; align manifest | Approve drafts internally
Mammoet (MMT) | Method/stowage; simulations; deck ops; seafastening execution | Draft pack to OFCO | RA/MOS/PTW attachments
MWS | COA; suitability; attendance | Issue COA to OFCO/LCT | Confirm calculations vs Aries
LCT Bushra / KFS | Marine docs; voyage; mooring; ramp evidence | Master certs/PAN | Stability/voyage plan inputs
HM / AD Ports / Customs | Approvals | N/A | Review

## Ideas_extras
Topic | Recommendation
Single trip folder | Per TR: 00_Index + 01_PTWHM + 02_Marine + 03_Customs + 04_AGI + 99_Receipts
Revision SSOT | Filename: DOCID_rev_date_author; obsolete folder, not delete
Two-clock deadlines | Store UAE local + UTC columns for sail-away / COA cutoffs
Permit buffer | Request PTW validity to cover +7d weather/berth slip (project lesson)
Operator matrix | SPMT operator names ↔ gate pass IDs ↔ shift (avoid last-minute ID block)
Weather gate | Attach METAR/NCM snapshot ID to DOC-021 row when Go/No-Go
AGI exception path | Emergency voyages: separate tracker row; do not reuse normal TR checklist
Weekly governance | Friday 09:00: red rows in Master + berth + PTW expiry review